## Blad1
Failure Mode and Effects Analysis
FAILURE MODE AND EFFECTS ANALYSIS
Item: | Bio-Inspired Flying Vehicle |  |  |  | Responsibility: |  |  | Giacomo Demetrio Masone | FMEA number: | 10012
Model: | / |  |  |  | Prepared by: |  |  | Giacomo Demetrio Masone | Page : | 1 of 1
Core Team: | Masone, Ahmed, Gawan, Atreya, Guo, Begum, Mohamed and Tettey | [7 empty] | FMEA Date (Orig): | 2024-11-26
Process Function | Potential Failure Mode | Potential Effect(s) of Failure | Sev | Potential Cause(s)/ Mechanism(s) of Failure | Occur | Detec | RPN | Recommended Action(s) | Responsibility and Target Completion Date | Action Results
[10 empty] | Actions Taken | S | O | D | RPN
Wing Mechanism | Structural Fatigue | Cracks, or breakage | 5 | Continuous cyclic stresses | 2 | 3 | 30 | Use fatigue-resistant materials | 2025-01-03 | Stress analysis | 4 | 4 | 1 | 16
| Actuation Failure | Overheating, overloading, or wear | 4 | Motors, or actuators controlling wing motion | 4 | 4 | 64 | Select actuators with high torque and durability | 2025-01-11 | Implement thermal protection systems | 5 | 3 | 2 | 30
| Aerodynamic Inefficiency | Reducing lift, or causing loss of control | 4 | High aerodynamic loads | 4 | 1 | 16 | Incorporate stiffeners, or hybrid structures | 2025-02-02 | Test for load endurance | 5 | 3 | 1 | 15
Power System | Battery Depletion | Premature battery depletion | 3 | Insufficient energy storage | 5 | 5 | 75 | Use high-energy-density batteries | 2025-01-21 | Consider solar charging for extended flights | 3 | 3 | 3 | 27
| Overheating | Thermal runaway, or reduced efficiency | 4 | Excessive heat generation | 3 | 5 | 60 | Incorporate heat sinks | 2025-02-04 | Thermal monitoring sensors | 4 | 2 | 4 | 32
| Insufficient Power Delivery | Erratic wing, or propulsion behavior | 5 | Voltage drops | 2 | 6 | 60 | Implement power distribution units | 2025-01-01 | Voltage regulation and redundancy | 4 | 3 | 2 | 24
Control System | Sensor Malfunction | Incorrect feedback for the flight control system | 4 | Sensors used for navigation | 1 | 2 | 8 | Use redundant sensors | 2025-02-10 | Implement sensor fusion algorithms | 3 | 4 | 2 | 24
| Algorithm Instability | Unstable flight behavior, or a complete loss of control | 5 | Bugs, or inaccuracies in the control algorithm | 4 | 1 | 20 | Test control algorithms | 2025-03-08 | Use adaptive control algorithms | 2 | 5 | 2 | 20
| Communication Interference | Loss of control or misnavigation | 5 | Loss of communication between the vehicle and its ground station | 5 | 4 | 100 | Implement redundant communication channels | 2025-02-14 | Maintain reliable data transmission | 5 | 5 | 1 | 25